## Gantt
Software Design Specification Timeline - Food Delivery
Group 8
Project start date: | 2023-09-25
[5 empty] | September | [5 empty] | October
[5 empty] | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03
Assignment | Member | Progress | Start | Days | M | T | W | Th | F | Sa | Su | M | T | W
Class: Registered User
Description | Justin Mendillo | 100% | 2023-09-25 | 6
Atributes | Justin Mendillo | 100% | 2023-09-25 | 8
Operations | Justin Mendillo | 100% | 2023-09-25 | 6
Class: Delivery Driver
Description | Justin Mendillo | 100% | 2023-09-25 | 6
Atributes | Christopher Santos | 100% | 2023-09-25 | 10
Operations | Christopher Santos | 100% | 2023-09-25 | 6
Restaurant
Description | Justin Mendillo | 100% | 2023-09-25 | 7
Atributes | Justin Mendillo | 100% | 2023-09-25 | 7
Operations | Christopher Santos | 100% | 2023-09-25 | 9
Payment
Description | Christopher Santos | 100% | 2023-09-25 | 9
Atributes | Justin Mendillo | 100% | 2023-09-25 | 6
Operations | Christopher Santos | 100% | 2023-09-25 | 6
Admin
Description | Justin Mendillo | 100% | 2023-09-25 | 6
Atributes | Justin Mendillo | 100% | 2023-09-25 | 8
Operations | Christopher Santos | 100% | 2023-09-25 | 9
Make Order
Description | Justin Mendillo | 100% | 2023-09-25 | 6
Atributes | Justin Mendillo | 100% | 2023-09-25 | 8
Operations | Christopher Santos | 100% | 2023-09-25 | 9
Architecture
| Ravien Gamalinda | 100% | 2023-09-25 | 8
Diagrams
| Justin Mendillo | 100% | 2023-09-25 | 8
Gantt Timeline
| Chiewant Reat | 100% | 2023-09-25 | 10
To add more data, Insert new rows ABOVE this one